## Week 8
Project Title: CardioCare Quest |  |  |  |  | Report for | Week 11 (Mar 30 - Apr 3)
Team Members:
| Jesse Ceja | Anna Cheatham | Tyler Jeffrey | Rique Trujillo Yazzie
XXX
Task ID | Status | Description |  |  | Assigned to | Start Date | Start Week | Expected End Date | Finished on Week | Measurable Outcome | Actual Outcome | XXX
N/A | <pick a status from the list> | <2-3 sentences to describe what is involved with the task and its goals in more detail> |  |  | <who’s responsible; if multiple persons, to what percentage> | <date task created> | <pick a week from the list> | <date task is due> | <pick a week from the list> | <Concise statement of exactly what deliverable is expected with notes on expectations of quality and/or completion> | <Concise statement of exactly what was delivered and at what level of quality>
1 | In progress | Meeting with Pavan, sharing UI design concepts and symposium presentation materials. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie, Group meeting: 25% each | 2026-03-23 | Week 10 (Mar 23 - Mar 27) | 2026-04-01 |  | Get updated feedback from the client on UI design concepts for the app shell. Also discussing poster and abstract for presentation. |  | XXX
2 | In progress | Presentation Materials: Abstract. |  |  | Anna Cheatham | 2026-03-23 | Week 10 (Mar 23 - Mar 27) | 2026-04-02 |  | Finalizing the project abstract for our presentation, this includes a medium-length description of problem, solution, and project vision. |  | XXX
3 | In progress | Finalized technology feasibility document. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. Members will be working within their previously assigned sections. | 2026-03-26 | Week 10 (Mar 23 - Mar 27) | 2026-04-03 |  | Following document review, each section of this document will be fully fleshed out in terms of content and formatting. |  | XXX
4 | Done | Requirements Document planning. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. | 2026-03-26 | Week 10 (Mar 23 - Mar 27) | 2026-04-01 | Week 10 (Mar 23 - Mar 27) | Plan out sections for the requirements document as well as meetings that will have to be scheduled with project teams. | Sections for the document have been laid out and assigned to members. Requirements talks with client will be carried out within the next few weeks. | XXX
5 | In progress | Finalizing Presentation Materials for Undergrad Symposium. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. Specific portions will be outlined in tasks below. | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-17 |  | Finalize and submit all materials required for symposium: abstract, poster, and demo. |  | XXX
6 | In progress | Presentation Materials: Database configuration |  |  | Jesse Ceja | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-02 |  | Setup and host a cloud database for collecting user id's and step counts. |  | XXX
7 | In progress | Presentation Materials: Website design |  |  | Rique Yazzie | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-02 |  | Personalize the database website to be more visually appealing via CSS and Bootstrap. |  | XXX
8 | In progress | Presentation Materials: Twine demo/integration |  |  | Tyler Jeffrey | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-02 |  | Integrate Twine with the database, allowing data to be passed via Twine actions. Develop a functioning Twine experience that meets the basic requirements for a demo. |  | XXX
9 | In progress | Presentation Materials: Poster design |  |  | Anna Cheatham | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-02 |  | Map out poster design and flow. Will be using Canva to create and edit the poster. |  | XXX
10 | Next up | Team Progress Update |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. | 2026-04-02 | Week 11 (Mar 30 - Apr 3) | 2026-04-09 |  | Create an outline or presentation of the required topics for team updates. |  | XXX
11 | Next up | Twine Game Planning |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. | 2026-04-02 | Week 11 (Mar 30 - Apr 3) | 2026-04-09 |  | Begin planning ideas for each of the Twine topics we have to make. This includes a general game loop and rough visual experience. |  | XXX
12 | [11 empty] | XXX
13 | [11 empty] | XXX
14 | [11 empty] | XXX
15 | [11 empty] | XXX
16 | [11 empty] | XXX
17 | [11 empty] | XXX
18 | [11 empty] | XXX
19 | [11 empty] | XXX
20 | [11 empty] | XXX
21 | [11 empty] | XXX
22 | [11 empty] | XXX
23 | [11 empty] | XXX
24 | [11 empty] | XXX
25 | [11 empty] | XXX
26 | [11 empty] | XXX
27 | [11 empty] | XXX
28 | [11 empty] | XXX
29 | [11 empty] | XXX
30 | [11 empty] | XXX
31 | [11 empty] | XXX
32 | [11 empty] | XXX
33 | [11 empty] | XXX
34 | [11 empty] | XXX
35 | [11 empty] | XXX
36 | [11 empty] | XXX
37 | [11 empty] | XXX
38 | [11 empty] | XXX
39 | [11 empty] | XXX
40 | [11 empty] | XXX
41 | [11 empty] | XXX
42 | [11 empty] | XXX
43 | [11 empty] | XXX
44 | [11 empty] | XXX
45 | [11 empty] | XXX
46 | [11 empty] | XXX
47 | [11 empty] | XXX
48 | [11 empty] | XXX
49 | [11 empty] | XXX
50 | [11 empty] | XXX
51 | [11 empty] | XXX
52 | [11 empty] | XXX
53 | [11 empty] | XXX
54 | [11 empty] | XXX
55 | [11 empty] | XXX
56 | [11 empty] | XXX
57 | [11 empty] | XXX
58 | [11 empty] | XXX
59 | [11 empty] | XXX
60 | [11 empty] | XXX
61 | [11 empty] | XXX
62 | [11 empty] | XXX
63 | [11 empty] | XXX
64 | [11 empty] | XXX
65 | [11 empty] | XXX
66 | [11 empty] | XXX
67 | [11 empty] | XXX
68 | [11 empty] | XXX
69 | [11 empty] | XXX
70 | [11 empty] | XXX
71 | [11 empty] | XXX
72 | [11 empty] | XXX
73 | [11 empty] | XXX
74 | [11 empty] | XXX
75 | [11 empty] | XXX
76 | [11 empty] | XXX
77 | [11 empty] | XXX
78 | [11 empty] | XXX

## Sheet2
Status | Week
<pick a status from the list> | <pick a week from the list>
Done | Week 4 (Feb 2 - Feb 6)
In progress | Week 5 (Feb 9 - Feb 13)
Overdue | Week 6 (Feb 16 - Feb 20)
Next up | Week 7 (Feb 23 - Feb 27)
Week 8 (Mar 2 - Mar 6)
Week 9 (Mar 16 - Mar 20)
Week 10 (Mar 23 - Mar 27)
Week 11 (Mar 30 - Apr 3)
Week 12 (Apr 6 - Apr 10)
Week 13 (Apr 13 - Apr 17)
Week 14 (Apr 20 - Apr 24)
Week 15 (Apr 27 - May 1)
Week 15 (Apr 27 - May 1)