## Week 8
Project Title: CardioCare Quest |  |  |  |  | Report for | Week 10 (Mar 23 - Mar 27)
Team Members:
| Jesse Ceja | Anna Cheatham | Tyler Jeffrey | Rique Trujillo Yazzie
XXX
Task ID | Status | Description |  |  | Assigned to | Start Date | Start Week | Expected End Date | Finished on Week | Measurable Outcome | Actual Outcome | XXX
N/A | <pick a status from the list> | <2-3 sentences to describe what is involved with the task and its goals in more detail> |  |  | <who’s responsible; if multiple persons, to what percentage> | <date task created> | <pick a week from the list> | <date task is due> | <pick a week from the list> | <Concise statement of exactly what deliverable is expected with notes on expectations of quality and/or completion> | <Concise statement of exactly what was delivered and at what level of quality>
1 | Done | Meeting with client, Jared Duval. Discussing project requirements & merger with NetGauge. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie, Group meeting: 25% each | 2026-03-03 | Week 8 (Mar 2 - Mar 6) | 2026-03-18 | Week 9 (Mar 16 - Mar 20) | Getting an updated list of project requirements and discussing the changes as a result of the project merger. | Discussed updated project requirements. Presented prototype UI design and began laying out the GitHub project structure in tandem with NetGauge project. | XXX
2 | Done | Meeting with CardioCare Quest team lead, Pavan Gorintla. Discussing merger and project changes. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie, Group meeting: 25% each | 2026-03-03 | Week 8 (Mar 2 - Mar 6) | 2026-03-25 | Week 9 (Mar 16 - Mar 20) | Understanding how CardioCare Quest will integrate with the workflow of NetGauge. Understanding project requirements further. | Discussed project timeline for deliverables. Confirmed GitHub changes for project. Also discussed symposium presentation materials. | XXX
3 | Done | Technology Feasibility Document Draft. This document will help us to refine the project's technological feasibility. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. Members will be assigned portions of the document as listed below. | 2026-03-05 | Week 8 (Mar 2 - Mar 6) | 2026-03-22 | Week 9 (Mar 16 - Mar 20) | Produce a document that identifies key architectural challenges and selects a solutions for each. validated by an analysis and steps for technological integration. | We have created a mostly finalized draft going over an investigation into the project's major technical challenges and analyzed their solutions. | XXX
4 | Done | Aspects of Technological Feasibility Draft: Challenge 1 and all related sections & Conclusion |  |  | Jesse Ceja | 2026-03-05 | Week 8 (Mar 2 - Mar 6) | 2026-03-19 | Week 9 (Mar 16 - Mar 20) | Parts listed have the majority of detail needed, proper formatting may be missing for draft but core information is conveyed. | Assigned challenge has been completed with all sections accounted for. | XXX
5 | Done | Aspects of Technological Feasibility Draft: Challenge 2 & Integration |  |  | Rique Yazzie | 2026-03-05 | Week 8 (Mar 2 - Mar 6) | 2026-03-19 | Week 9 (Mar 16 - Mar 20) | Parts listed have the majority of detail needed, proper formatting may be missing for draft but core information is conveyed. | Assigned challenge has been completed with all sections accounted for. | XXX
6 | Done | Aspects of Technological Feasibility Draft: Challenge 4, Introduction, & Technogical Challenges |  |  | Tyler Jeffrey | 2026-03-05 | Week 8 (Mar 2 - Mar 6) | 2026-03-19 | Week 9 (Mar 16 - Mar 20) | Parts listed have the majority of detail needed, proper formatting may be missing for draft but core information is conveyed. | Assigned challenge has been completed with all sections accounted for. | XXX
7 | Done | Aspects of Technological Feasibility Draft: Challenge 3 & Integration. |  |  | Anna Cheatham | 2026-03-05 | Week 8 (Mar 2 - Mar 6) | 2026-03-19 | Week 9 (Mar 16 - Mar 20) | Parts listed have the majority of detail needed, proper formatting may be missing for draft but core information is conveyed. | Assigned challenge has been completed with all sections accounted for. | XXX
8 | In progress | Meeting with Pavan, sharing UI design concepts and symposium presentation materials. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie, Group meeting: 25% each | 2026-03-23 | Week 10 (Mar 23 - Mar 27) | 2026-04-01 |  | Get updated feedback from the client on UI design concepts for the app shell. Also discussing poster and abstract for presentation. |  | XXX
9 | In progress | Project presentation preparation. Finalizing abstract. |  |  | Anna Cheatham | 2026-03-23 | Week 10 (Mar 23 - Mar 27) | 2026-04-01 |  | Finalizing the project abstract for our presentation, this includes a medium-length description of problem, solution, and project vision. |  | XXX
10 | Next up | Finalized technology feasibility document. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. Members will be working within their previously assigned sections. | 2026-03-26 | Week 10 (Mar 23 - Mar 27) | 2026-04-03 |  | Following document review, each section of this document will be fully fleshed out in terms of content and formatting. |  | XXX
11 | Next up | Requirements Document planning. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. Members will be working within their previously assigned sections. | 2026-03-26 | Week 10 (Mar 23 - Mar 27) | 2026-04-01 |  | Plan out sections for the requirements document as well as meetings that will have to be scheduled with project teams. |  | XXX
12 | [11 empty] | XXX
13 | [11 empty] | XXX
14 | [11 empty] | XXX
15 | [11 empty] | XXX
16 | [11 empty] | XXX
17 | [11 empty] | XXX
18 | [11 empty] | XXX
19 | [11 empty] | XXX
20 | [11 empty] | XXX
21 | [11 empty] | XXX
22 | [11 empty] | XXX
23 | [11 empty] | XXX
24 | [11 empty] | XXX
25 | [11 empty] | XXX
26 | [11 empty] | XXX
27 | [11 empty] | XXX
28 | [11 empty] | XXX
29 | [11 empty] | XXX
30 | [11 empty] | XXX
31 | [11 empty] | XXX
32 | [11 empty] | XXX
33 | [11 empty] | XXX
34 | [11 empty] | XXX
35 | [11 empty] | XXX
36 | [11 empty] | XXX
37 | [11 empty] | XXX
38 | [11 empty] | XXX
39 | [11 empty] | XXX
40 | [11 empty] | XXX
41 | [11 empty] | XXX
42 | [11 empty] | XXX
43 | [11 empty] | XXX
44 | [11 empty] | XXX
45 | [11 empty] | XXX
46 | [11 empty] | XXX
47 | [11 empty] | XXX
48 | [11 empty] | XXX
49 | [11 empty] | XXX
50 | [11 empty] | XXX
51 | [11 empty] | XXX
52 | [11 empty] | XXX
53 | [11 empty] | XXX
54 | [11 empty] | XXX
55 | [11 empty] | XXX
56 | [11 empty] | XXX
57 | [11 empty] | XXX
58 | [11 empty] | XXX
59 | [11 empty] | XXX
60 | [11 empty] | XXX
61 | [11 empty] | XXX
62 | [11 empty] | XXX
63 | [11 empty] | XXX
64 | [11 empty] | XXX
65 | [11 empty] | XXX
66 | [11 empty] | XXX
67 | [11 empty] | XXX
68 | [11 empty] | XXX
69 | [11 empty] | XXX
70 | [11 empty] | XXX
71 | [11 empty] | XXX
72 | [11 empty] | XXX
73 | [11 empty] | XXX
74 | [11 empty] | XXX
75 | [11 empty] | XXX
76 | [11 empty] | XXX
77 | [11 empty] | XXX
78 | [11 empty] | XXX

## Sheet2
Status | Week
<pick a status from the list> | <pick a week from the list>
Done | Week 4 (Feb 2 - Feb 6)
In progress | Week 5 (Feb 9 - Feb 13)
Overdue | Week 6 (Feb 16 - Feb 20)
Next up | Week 7 (Feb 23 - Feb 27)
Week 8 (Mar 2 - Mar 6)
Week 9 (Mar 16 - Mar 20)
Week 10 (Mar 23 - Mar 27)
Week 11 (Mar 30 - Apr 3)
Week 12 (Apr 6 - Apr 10)
Week 13 (Apr 13 - Apr 17)
Week 14 (Apr 20 - Apr 24)
Week 15 (Apr 27 - May 1)
Week 15 (Apr 27 - May 1)