## Week 8
Project Title: CardioCare Quest |  |  |  |  | Report for | Week 14 (Apr 20 - Apr 24)
Team Members:
| Jesse Ceja | Anna Cheatham | Tyler Jeffrey | Rique Trujillo Yazzie
XXX
Task ID | Status | Description |  |  | Assigned to | Start Date | Start Week | Expected End Date | Finished on Week | Measurable Outcome | Actual Outcome | XXX
N/A | <pick a status from the list> | <2-3 sentences to describe what is involved with the task and its goals in more detail> |  |  | <who’s responsible; if multiple persons, to what percentage> | <date task created> | <pick a week from the list> | <date task is due> | <pick a week from the list> | <Concise statement of exactly what deliverable is expected with notes on expectations of quality and/or completion> | <Concise statement of exactly what was delivered and at what level of quality>
1 | Done | Finalizing Presentation Materials for Undergrad Symposium. |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. Specific portions will be outlined in tasks below. | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-17 | Week 13 (Apr 13 - Apr 17) | Finalize and submit all materials required for symposium: abstract, poster, and demo. | All project materials for the symposium have been uploaded. This includes the following: abstract, demo, poster, and video recording. | XXX
2 | Done | Presentation Materials: Poster design |  |  | Anna Cheatham | 2026-03-29 | Week 11 (Mar 30 - Apr 3) | 2026-04-17 | Week 13 (Apr 13 - Apr 17) | Map out poster design and flow. Will be using Canva to create and edit the poster. | Poster has been completed and submitted. Design has been discussed with Pavan. | XXX
3 | Done | Requirements Document: Adherence Game |  |  | Anna Cheatham | 2026-04-02 | Week 11 (Mar 30 - Apr 3) | 2026-04-10 | Week 13 (Apr 13 - Apr 17) | Detail a list of functional and non-functional requirements for the Twine adherence game. | List of FR and NFR have been listed and detailed. | XXX
4 | Done | Requirements Document: Blood Pressure Game |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. | 2026-04-02 | Week 11 (Mar 30 - Apr 3) | 2026-04-16 | Week 13 (Apr 13 - Apr 17) | Detail a list of functional and non-functional requirements for the Twine blood pressure game. This includes every mini-game we will be implementing. | List of FR and NFR have been listed and detailed. | XXX
5 | Done | Meeting with CardioCare Quest team lead Pavan Gorintla |  |  | Tyler Jeffrey, Jesse Ceja, Anna Cheatham, Rique Yazzie. | 2026-04-15 | Week 13 (Apr 13 - Apr 17) | 2026-04-15 | Week 13 (Apr 13 - Apr 17) | Share game ideas and discuss our listed requirements. Also sharing symposium presentation materials. | Shared symposium materials and discussed game ideas. Walked through an example presentation. | XXX
6 | In progress | Design Review: Intro, Solution Overview, Key Reqs, Schedule |  |  | Tyler Jeffrey | 2026-04-19 | Week 14 (Apr 20 - Apr 24) | 2026-04-24 |  | Create and design presentation slides covering the outlined content. Ensure a consistent format and minimal wording. |  | XXX
7 | In progress | Design Review: Problem Statement, Risks & Feasibility |  |  | Jesse Ceja | 2026-04-19 | Week 14 (Apr 20 - Apr 24) | 2026-04-24 |  | Create and design presentation slides covering the outlined content. Ensure a consistent format and minimal wording. |  | XXX
8 | In progress | Design Review: Key Reqs, Conclusion |  |  | Anna Cheatham, Rique Yazzie | 2026-04-19 | Week 14 (Apr 20 - Apr 24) | 2026-04-24 |  | Create and design presentation slides covering the outlined content. Ensure a consistent format and minimala wording. |  | XXX
9 | In progress | Prototype Demo: Twine Development |  |  | Jesse Ceja, Tyler Jeffrey | 2026-04-19 | Week 14 (Apr 20 - Apr 24) | 2026-04-30 |  | Create a functioning Twine game prototype collecting exercise-related data and having it affect gameplay. |  | XXX
10 | In progress | Prototype Demo: Web Design |  |  | Rique Yazzie, Anna Cheatham | 2026-04-19 | Week 14 (Apr 20 - Apr 24) | 2026-04-30 |  | Polish the functioning prototype by adding CSS styling and importing any assets that may be required. |  | XXX
11 | Next up | Project Info Mini-Video |  |  | Tyler Jeffrey, Jesse Ceja, Rique Yazzie, Anna Cheatham | 2026-04-23 | Week 14 (Apr 20 - Apr 24) | 2026-04-30 |  | Create a ~2 minute elevator pitch video for the project. |  | XXX
12 | Next up | Meeting with CardioCare Quest team lead Pavan Gorintla |  |  | Tyler Jeffrey, Jesse Ceja, Rique Yazzie, Anna Cheatham | 2026-04-29 | Week 15 (Apr 27 - May 1) | 2026-04-29 |  | Showcase the requirements document and the functioning prototype. Begin looking at the next steps moving into the second semester of capstone. |  | XXX
13 | [11 empty] | XXX
14 | [11 empty] | XXX
15 | [11 empty] | XXX
16 | [11 empty] | XXX
17 | [11 empty] | XXX
18 | [11 empty] | XXX
19 | [11 empty] | XXX
20 | [11 empty] | XXX
21 | [11 empty] | XXX
22 | [11 empty] | XXX
23 | [11 empty] | XXX
24 | [11 empty] | XXX
25 | [11 empty] | XXX
26 | [11 empty] | XXX
27 | [11 empty] | XXX
28 | [11 empty] | XXX
29 | [11 empty] | XXX
30 | [11 empty] | XXX
31 | [11 empty] | XXX
32 | [11 empty] | XXX
33 | [11 empty] | XXX
34 | [11 empty] | XXX
35 | [11 empty] | XXX
36 | [11 empty] | XXX
37 | [11 empty] | XXX
38 | [11 empty] | XXX
39 | [11 empty] | XXX
40 | [11 empty] | XXX
41 | [11 empty] | XXX
42 | [11 empty] | XXX
43 | [11 empty] | XXX
44 | [11 empty] | XXX
45 | [11 empty] | XXX
46 | [11 empty] | XXX
47 | [11 empty] | XXX
48 | [11 empty] | XXX
49 | [11 empty] | XXX
50 | [11 empty] | XXX
51 | [11 empty] | XXX
52 | [11 empty] | XXX
53 | [11 empty] | XXX
54 | [11 empty] | XXX
55 | [11 empty] | XXX
56 | [11 empty] | XXX
57 | [11 empty] | XXX
58 | [11 empty] | XXX
59 | [11 empty] | XXX
60 | [11 empty] | XXX
61 | [11 empty] | XXX
62 | [11 empty] | XXX
63 | [11 empty] | XXX
64 | [11 empty] | XXX
65 | [11 empty] | XXX
66 | [11 empty] | XXX
67 | [11 empty] | XXX
68 | [11 empty] | XXX
69 | [11 empty] | XXX
70 | [11 empty] | XXX
71 | [11 empty] | XXX
72 | [11 empty] | XXX
73 | [11 empty] | XXX
74 | [11 empty] | XXX
75 | [11 empty] | XXX
76 | [11 empty] | XXX
77 | [11 empty] | XXX
78 | [11 empty] | XXX

## Sheet2
Status | Week
<pick a status from the list> | <pick a week from the list>
Done | Week 4 (Feb 2 - Feb 6)
In progress | Week 5 (Feb 9 - Feb 13)
Overdue | Week 6 (Feb 16 - Feb 20)
Next up | Week 7 (Feb 23 - Feb 27)
Week 8 (Mar 2 - Mar 6)
Week 9 (Mar 16 - Mar 20)
Week 10 (Mar 23 - Mar 27)
Week 11 (Mar 30 - Apr 3)
Week 12 (Apr 6 - Apr 10)
Week 13 (Apr 13 - Apr 17)
Week 14 (Apr 20 - Apr 24)
Week 15 (Apr 27 - May 1)
Week 15 (Apr 27 - May 1)